## Template
BUG ID | Module | Bug Title | Test Steps | Expected Result | Actual Result | Issue Type | Status | Priority | Severity | Reported By | Report Date
BUG-001 | Create Account | Application accepts mobile number greater than 10 digits during account creation | 1. Open Amazon India website. 2. Click on Create Account. 3. Enter a valid name. 4. Enter a mobile number with more than 10 digits. 5. Complete CAPTCHA if displayed. 6. Click Continue/Create Account. | The application should display a validation message and should not allow a mobile number with more than 10 digits. | The application accepted a mobile number with more than 10 digits and proceeded to the OTP verification page. | Bug | Open | High | Medium | Aranya dev | 2026-07-10
BUG-002 | Authentication / Create Account | Previously cleared mobile number is restored after page refresh on the Sign In page. | 1. Open the Amazon Sign In page. 2. Enter an invalid mobile number. 3. Click Continue. 4. Wait for the validation message. 5. Clear the mobile number field completely. 6. Refresh the page (F5). | The mobile number field should remain empty after the page refresh because the user has already cleared the input. | The previously entered invalid mobile number is restored automatically after the page refresh even though the input field was cleared before refreshing. | Bug | Open | Low | Low | Aranya dev | 2026-07-13
BUG-003 | Authentication / Create Account | Validation message persists after navigating back from the password page. | 1. Open the Amazon Sign In page. 2. Enter an invalid mobile number. 3. Click Continue. 4. Observe the validation message. 5. Enter a valid registered mobile number. 6. Click Continue to navigate to the password page. 7. Click the browser Back button. | The validation message should be cleared when the user returns to the Sign In page after successfully proceeding with a valid mobile number. | After navigating back from the password page, the valid mobile number remains in the input field; however, the previous "Invalid mobile number" validation message is still displayed. | Bug | Open | Medium | Low | Aranya dev | 2026-07-13